## WSJF calculation sheet
TMAP: Prioritization - Weighted Shortest Job First |  |  |  | © Sogeti 2024
Cost of Delay = Business Value + Time Criticality + Risk Reduction
WSJF = Cost of Delay / Duration
The highest WSJF gets the highest priority
Feature / Item | Business value | Time criticality | Risk reduction | Cost of Delay (calculated) | Duration / Job size | WSJF (calculated)
note1: see separate example & explanation sheet for guidance
note2: copy empty lines if you need to administer more features and/or items
See this page on TMAP.net for an explanation: https://tmap.net/building-blocks/Planning-the-delivery-DevOps
Note on A6: Short description of the feature or backlog item
Note on B6: Indicates the importance for stakeholders. But also indicates risk when the realization of the item is delayed.
Note on C6: Indicates how the business value decreases as time passes and considers milestones that must be achieved.
Note on D6: Recognizes the extent to which this item removes risk in this or a future delivery.
Note on E6: Cost of delay is calculated using the business value, time criticality and risk reduction from the previous columns.
Note on F6: The time needed to realize the item. When difficult to determine, size in story points is a good indicator.
Note on G6: The WSJF is calculated by dividing the Cost of Delay by Duration. The feature/item with the highest value must be done first (indicated by the darkest color)

## WSJF example & explanation
TMAP: Prioritization - Weighted Shortest Job First |  |  |  | © Sogeti 2024
The WSJF is a prioritization model used to sequence the backlog items by calculation using the relative cost of delay and duration.
Cost of Delay = Business Value + Time Criticality + Risk Reduction (indicated by numbers on a Fibonacci scale)
WSJF = Cost of Delay / Duration
The highest WSJF gets the highest priority
Feature / Item | Business value | Time criticality | Risk reduction | Cost of Delay (calculated) | Duration / Job size | WSJF (calculated)
Register choice | 3 | 1 | 2 | 6 | 3 | 2
Process choice | 1 | 3 | 5 | 9 | 3 | 3
Show choice | 5 | 2 | 5 | 12 | 3 | 4
Edit choice | 3 | 8 | 1 | 12 | 4 | 3
Please note that this table is different than in the book, this has the features/items as rows, in the book the features/items are in columns, so the table is 90 degrees turned.
Note on A7: Short description of the feature or backlog item
Note on B7: Indicates the importance for stakeholders. But also indicates risk when the realization of the item is delayed.
Note on C7: Indicates how the business value decreases as time passes and considers milestones that must be achieved.
Note on D7: Recognizes the extent to which this item removes risk in this or a future delivery.
Note on E7: Cost of delay is calculated using the business value, time criticality and risk reduction from the previous columns.
Note on F7: The time needed to realize the item. When difficult to determine, size in story points is a good indicator.
Note on G7: The WSJF is calculated by dividing the Cost of Delay by Duration. The feature/item with the highest value must be done first (indicated by the darkest color)