## Transition based on topics
Template to support the transition from one IT-delivery model to another, based on "Quality Engineering Topics" | [7 empty] | © Sogeti / TMAP 2024
description available?
Group | Topic | as-is situation | to-be situation | Effort level for transition | Description how the transition will be done | Status of transition | Comments / description of status / remarks
Organizing topics
| Quality & Test policy | No | No
| Responsibilities & Roles | No | No
| Monitoring & Control | No | No
| Anomaly management | No | No
| Reporting & Alerting | No | No
| Estimating | No | No
| Planning | No | No
| Infrastructure | No | No
| Tooling | No | No
| Metrics | No | No
| Continuous improvement | No | No
Performing topics
| Quality risk analysis & Test strategy | No | No
| Acceptance criteria | No | No
| Quality measures | No | No
| Reviewing | No | No
| Test design | No | No
| Test data management | No | No
| Test automation | No | No
| Test execution | No | No
| Investigate & Assess outcome | No | No

## Explanation of template
Template to support the transition from one IT-delivery model to another, based on "Quality Engineering Topics" © Sogeti / TMAP 2024
Tracking progress of the transition
In the transition table the status of the transition is tracked for each of the topics. Per topic a status is indicated and remarks or comments for the status elaborate the current situation. In general, a transition will take some time and usually the IT delivery work is just carried on because the business can’t be postponed for the time needed to do an implementation. This may require some extra attention during the transition because intermediate situations will exist where the transition has already started but is not yet completed.
Each QA & testing topic represents a number of activities. In every situation the people involved need to define how these activities are implemented and executed. In the ideal world a description is available of how each of the quality engineering topics is implemented in the “as-is” situation. If such description is not available or not described in sufficient detail, then you will need to organize to come to a sufficient description of the current situation. Next the implementation of the quality engineering topics for the “to-be” situation must be defined. This means that for each topic the team(s) involved must define how they will approach the activities of that topic. When the “as-is” and “to-be” situations are described, you can compare them and decide if the transition for each topic will be easy or difficult. Based on this also the transition order is worked out. Preferably several topics will be transitioning in parallel. To create a clear overview for everyone involved the result can be communicated using a table (the available TMAP template can be used for this purpose). The descriptions in chapters 11 through 14 in the book are helpful in creating the descriptions of the current and future situations.

## Example
Template to support the transition from one IT-delivery model to another, based on "Quality Engineering Topics" | [7 empty] | © Sogeti / TMAP 2024
THIS PAGE CONTAINS THE EXAMPLE THAT IS USED IN THE SYLLABUS OF THE TRAINING COURSE TMAP:Organizing Built-in Quality At Scale
description available?
Group | Topic | as-is situation | to-be situation | Effort level for transition | Description how the transition will be done | Status of transition | Comments / description of status / remarks
Organizing topics
Quality & Test policy
Responsibilities & Roles
Monitoring & Control
Anomaly management
Reporting & Alerting
Estimating
Planning
Infrastructure
| Tooling | Yes | Yes | Intermediate | Existing tools will remain in use, new tools will be implemented by the operations-role in the team. | In progress | Team is currently working on getting user stories in Jira.
| Metrics | Yes | Partly | Difficult | Basic set of key metrics on release train level will be defined. Individual teams will conduct workshops to select aditional metrics and define how to collect te metrics | In progress | Basic set currently in development
| Continuous improvement | No | No | Intermediate | T.b.d. | Not started | Involvemend of scrum master community required
Performing topics
Quality risk analysis & Test strategy
Acceptance criteria
Quality measures
Reviewing
Test design
Test data management
Test automation
Test execution
Investigate & Assess outcome
note: other topics are currently hidden.