## TestPlan Sequential IT delivery (hidden)
TMAP: Test Plan Table
Note: this template focuses on Sequential IT delivery such as V-model-based and Waterfall
<<< nog te maken op basis van TMAP NEXT >>>

## Test Plan introduction
TMAP: Test Plan Template | © Sogeti 2022
Introduction.
In Sequential IT delivery (Waterfall and V-model) a separate test plan document is common.
In high-performance IT delivery usually there will not be a separate document for a test plan, the quality engineering and testing tasks will be integrated with other tasks on the team board.
Test plan definition (from the TMAP glossary on www.TMAP.net):
Description of the general structure and the choices with respect to the tests to be executed and the way to supply information. The test plan forms the reference during organizing and performing of the tests and also serves as an instrument to communicate with the client. The test plan is a description of the test project, including a description of the activities and the planning.
(So a testplan is NOT a description of the tests, e.g. test cases, themselves.)
The test plan in high-performance IT delivery (Agile / Scrum / DevOps):
In general a test plan is about what has to be done and when.
In high-performance IT delivery the "what" refers to the activities to be done. The activities are related to the QA&Testing topics of TMAP. The generic activities are partly described in the "Generic Test Agreements".
The specific activities should be described as tasks for the relevant team. These tasks are included on the Scrum board, Kanban board or other kind of team board, where the progress of the tasks is tracked.
To organize and describe the Quality Engineering & Testing activities 3 (groups of) documents are relevant: At the highest level the Quality & Test policy describes general principles, approaches and objectives for the organization. These are translated into Generic Test Agreements that relate to multiple releases or projects. The operational activities are described in a Test Plan.

## Example Test Plan
TMAP: Test Plan - Tasks on the Team board |  |  |  | © Sogeti 2022
IT delivery item | Task (e.g. applying quality measures) | ToDo | In progress | Done
Generic task: Test infrastructure | Create Infrastructure-as-Code to set up environment |  | X
Generic task: Test infrastructure | Run Infrastructure-as-Code to create the environment | X
User Story 1: Enter customer data | Test design using Decision Tables |  |  | X
User Story 1: Enter customer data | Test automation, creating test script |  | X
User Story 1: Enter customer data | Automated test execution of test scenarios | X
User Story 1: Enter customer data | Exploratory testing by team member and end user | X
User Story 1: Enter customer data | Performance testing using tooling | X
User Story 2: Creating notification letter to customer | Test design using Boundary Value Analysis | X
User Story 2: Creating notification letter to customer | Manual execution of test scenarios | X
User Story 2: Creating notification letter to customer | Usability testing of layout of letter | X
Note: this template focuses on High Performance IT delivery, for example Scrum, Agile, DevOps etc.
Note: usually there will not be a separate document for a test plan in high performance IT delivery, the tasks will be integrated with other tasks on the team board (such as Scrum board or Kanban board)
Note: These tasks are just a few examples. In your project you will probably have many more tasks. And you may have more granular or more general tasks.

## Test Plan template
As described on the previous sheets, it is not common to have a separate task board for testing tasks.
Please include the quality engineering and testing tasks in the task board you commonly use.
(for example in Jira, in Azure-DevOps, or any other tooling for Scrum boards, Kanban boards etcetera)